## Gantt Chart
Task Number | Task | Nov 2 - Nov 8 | Nov 9 - Nov 15 | Nov 16 - Nov 22 | Nov 23 - Nov 29 | Nov 30 - Dec 6 | Dec 7 - Dec 13 | Dec 14 - Dec 20 | Dec 21 - Dec 27 | Dec 28 - Jan 3 | Jan 4 - Jan 10 | Jan 11 - Jan 17 | Jan 18 - Jan 24 | Jan 25 - Jan 31 | Feb 1 - Feb 7 | Feb 8 - Feb 14 | Feb 15 - Feb 21 | Feb 22 - Feb 28 | Mar 1 - Mar 7 | Mar 8 - Mar 14 | Mar 15 - Mar 21
Design
1 | Design of boost converter |  | Mitchell
2 | Implement current & voltage sensors |  | Jaden
3 | Design of battery protection circuit |  | Tim
4 | Implement µC |  |  | All
| Order and wait for PCB to arrive | [5 empty] | All
| Program PCB | [5 empty] | All
Testing
| Test voltage regulators | [7 empty] | Mitchell
| Test protection circuits | [9 empty] | Jaden
| Test battery charge controller | [11 empty] | Tim
| DITL with external source | [13 empty] | All
| DITL with PV panels | [14 empty] | All
Integration
| Integrate with other bus components | [15 empty] | Mitchell
Note on B9: Mitchell Au: Budget $200
Note on B14: Mitchell Au: Consider thermal runaway Look at pumpkin